## Bug Log_Iteration2
Bug metric
No. | Iteration | Function | Description | Cause | Date Found | Date Solved | Severity | Points Allocation | Points Accumlated Per Iteration | Status | Action | Pair Programmers | Git Commit ID
1 | 2 | Bootstrap | BootstrapServlet is unable to unzip files with subdirectries | BootstrapServlet unzipFile method does not properly created subdirectories in the zip file. Treats all contents of the zip file as a file | 2017-09-22 | 2017-09-22 | Low | 1 | 1 | Resolved | Solved during planned debugging time | TMS + CBH | 8fa16f7065fe56861992b2e96b567fce28cbffcd
2 | 2 | Bootstrap | BootStrapServlet is unable to delete unzip files | BootstrapManager import methods did not close CSVReader | 2017-09-22 | 2017-09-22 | Low | 1 | 2 | Resolved | Solved during planned debugging time | TMS + CBH | 8fa16f7065fe56861992b2e96b567fce28cbffcd
3 | 2 | Bootstrap | BootstrapServlet JSON response does not reflect numbers of sucessful inserts into the database | BootstrapManager importLocationLookupCSV method does not add int returned by LocationDAO.insert method to the counter | 2017-09-22 | 2017-09-22 | High | 5 | 7 | Resolved | Solved during planned debugging time | TMS + CBH | c8b17b187aabebb5553e3b448f85d445b8431816
4 | 2 | Bootstrap | BootstrapServlet throws a NullPointerException when trying to retrieve error messages from BootstrapResult objects BootstrapManager import methods returns BootstrapResult with null error message hashmap | Line in BootstrapResult Constructor "this.allErrMsgs = this.allErrMsgs;" | 2017-09-22 | 2017-09-22 | High | 5 | 12 | Resolved | Solved during planned debugging time | TMS + CBH | c8b17b187aabebb5553e3b448f85d445b8431816
5 | 2 | Bootstrap | timstamp inserted with wrong values into the database | DATE_FORMAT_PATTERN field in Location.java is wrong | 2017-09-22 | 2017-09-22 | Critical | 10 | 22 | Resolved | Solved during planned debugging time | TMS + CBH | 9c48a0e1e3a168d6f41dbce673d5b6f6b8e53ce0
6 | 2 | Bootstrap | BootstrapServlet wrongly sets status attribute to "success" when it should be "error" | Number of errors were not checked before adding in the "error" attribute to the JSONObject | 2017-09-22 | 2017-09-22 | Low | 1 | 23 | Resolved | Solved during planned debugging time | TMS + CBH | 9c48a0e1e3a168d6f41dbce673d5b6f6b8e53ce0
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Bug_Log_Iteration3
Bug metric
No. | Iteration | Function | Description | Cause | Date Found | Date Solved | Severity | Points Allocation | Points Accumlated Per Iteration | Status | Action | Pair Programmers | Git Commit ID
1 | 3 | Top-K Next Place | JSON in wrong format, Semantic Place json attribute stores value as JSONArray where it should be String | Places with same ranks are stored in a JSONArray instead of returning as multiple JSONObjects with same ranks | 2017-10-07 | 2017-10-09 | Low | 1 | 1 | resolved | Replace popular place as JSONPopularPlace | Colin, Brit | 4330c7f2f3ac6857eab3f99fd0774e0ff8bcfea5
2 | 3 | Top-K Next Place | TopKNextPlaceview.jsp: In the case of Semantic Places with the same rank, only 1 is displayed | se.sql for table creation set password column of Demographic table as unique. Resulting in errors in inserting test cases | 2017-10-07 | 2017-10-09 | High | 5 | 6 | resolved | Remade the table | Colin, Brit | 4330c7f2f3ac6857eab3f99fd0774e0ff8bcfea6
3 | 3 | Top-K Next Place | view.jsp: total users are not displayed | Did not display total users | 2017-10-07 | 2017-10-09 | High | 5 | 11 | resolved | Remade the table | Colin, Brit | 4330c7f2f3ac6857eab3f99fd0774e0ff8bcfea7
4 | 3 | Top-K Next Place | Json response incorrectly states total number of users | se.sql for table creation set password column of Demographic table as unique. Resulting in errors in inserting test cases | 2017-10-07 | 2017-10-09 | High | 5 | 16 | resolved | DemographicDAO changed so that password not unique | Colin, Brit | 4330c7f2f3ac6857eab3f99fd0774e0ff8bcfea8
5 | 3 | Top-K Next Place | JSON response contains null value where no values should be found in "result" attribute. In the case where no results are found |  | 2017-10-07 | 2017-10-09 | High | 5 | 21 | resolved |  | Colin, Brit | 4330c7f2f3ac6857eab3f99fd0774e0ff8bcfea9
6 | 3 | Top-K Companion | Form action attribute points to wrong path |  | 2017-10-07 | 2017-10-08 | HIgh | 5 | 26 | resolved | Filled up form action | Colin, Zr | ae516257c47960539d0466708fd287e2647721b7
7 | 3 | Top-K Companion | TopKCompanionsJSONServlet missing | Servlet accidentally deleted when pushing to GIT | 2017-10-07 | 2017-10-08 | Critical | 10 | 36 | resolved | Filled up servlet | Colin, Zr | ae516257c47960539d0466708fd287e2647721b7
8 | 3 | Bootstrap | Bootstrap speed too slow, according to Rajesh it should be completed in seconds | Not using HashMap to check for duplicates but instead inserting row by row | 2017-10-07 | 2017-10-09 | Critical | 10 | 46 | resolved | Update new file reading method | ZhengRen, MingSheng
9 | 3 | Top-K Popular Place | JSON service returns error "invalid k" when k is not given, where it should be k = 3 by default | Did not set k=3 as default value | 2017-10-07 | 2017-10-10 | High | 5 | 51 | resolved | Set k = 3 in TopKPopularPlacesController | Colin, Brit
10 | 3 | Top-K Popular Place | JSON service returns JSONObject with attribute "semantic_place" with a JSONArray attribute in the case of two places sharing the same rank. Two separate JSONObjects should be returned instead | Incorrect data type | 2017-10-07 | 2017-10-10 | High | 5 | 56 | resolved | Edited data type | Colin, Brit
11 | 3 | Top-K Companion | TopKCompanionsController.java request.getParameter for mac-address was not tallying with the parameter name stated in the form | URL Mapping of TopKCompanionsController.java and TopKCompanionsJSONController swapped | 2017-10-08 | 2017-10-09 | Low | 1 | 57 | resolved | Swapped URL Mapping of TopKCompanionsController.java and TopKCompanionsJSONController | David, Brit | 86b6c6eda4df6565a8da624fb752b213da7fb11f
12 | 3 | Top-K Companion | TopKCompanionsController unescessarily validates for JSON token in request | URL Mapping of TopKCompanionsController.java and TopKCompanionsJSONController swapped | 2017-10-08 | 2017-10-10 | Low | 1 | 58 | resolved | Swapped URL Mapping of TopKCompanionsController.java and TopKCompanionsJSONController | David, Brit | 86b6c6eda4df6565a8da624fb752b213da7fb11f
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
116

## Bug_Log_Iteration4
Bug metric
No. | Iteration | Function | Description | Cause | Date Found | Date Solved | Severity | Points Allocation | Points Accumlated Per Iteration | Status | Action | Pair Programmers | Git Commit ID
1 | 4 | Login | Password validation not case sensitive | In SQL, `string`=`STRING` is true | 2017-10-09 | 2017-10-09 | High | 5 | 5 | resolved | Bug solved during PP when discovered | David, Brit | c64cfa7864325bd6133b5f4b35c99a9026de988e
2 | 4 | Basic Location Report | BreakdownController.java wrongly validates datetime form parameter. If number of seconds is selcted as 00, parameter passed will be "YYYY-MM-DDTHH:MM". If number of seconds is not 1,"YYYY-MM-DDTHH:MM:SS" |  | 2017-10-12 | 2017-12-10 | Low | 1 | 6 | resolved | Bug scheduled to fixed on pp task 4.14 | ZhengRen,MingSheng | 1d00d66add7c3254450eb1ff2cd9f999b337277e
3 | 4 | Bootstrap | Hard coding is required to handle JDBC connections on local and AWS | App does not detect if it is on local or AWS | 2017-10-09 | 2017-12-10 | Low | 1 | 7 | resolved | Bug scheduled to fixed on pp task 4.14 | ZhengRen,MingSheng | 1d00d66add7c3254450eb1ff2cd9f999b337277e
4 | 4 | Top-K Companion | TopKCompanionView.jsp form action points to "http://localhost:8084/app/top-k-companions", should be relative path "top-k-companions" | Non relative action field in <form> | 2017-10-09 | 2017-12-10 | High | 5 | 12 | resolved | Bug scheduled to fixed on pp task 4.14 | ZhengRen,MingSheng | 1d00d66add7c3254450eb1ff2cd9f999b337277e
5 | 4 | Top-K Next Place | JSON service returns wrong error message in the case of missing or blank fields | Error in if else logic for field validation | 2017-10-11 | 2017-12-10 | Low | 1 | 13 | resolved | Bug solved during PP when discovered | ZhengRen, David | 5f3eeb66207d299ce04f0cdc696d161fa0c90d15
6 | 4 | Top-K Next Place | Number of next-place-users counted wrongly | users who did not stay at a location for at least 5 minutes were counted as well | 2017-10-11 | 2017-12-10 | High | 5 | 18 | resolved | Bug solved during PP when discovered | ZhengRen, David | 5f3eeb66207d299ce04f0cdc696d161fa0c90d15
7 | 4 | Top-K Next Place | TopKNextPlacesView.jsp does not display any output after bug fix for errors 4.5 and 4.6 | Line 132, url.equals(url1) not url.equals(url2) | 2017-10-11 | 2017-12-10 | HIgh | 5 | 23 | resolved | Bug to be fixed during next pair programming session, task 4.13 on 10/12/2017 | ZhengRen,MingSheng | 1d00d66add7c3254450eb1ff2cd9f999b337277e
8 | 4 | Top-K Next Place | Function fails to detect users who spent more than 5 minutes at a location | LocationChunks were fragmented, a users stay at a location could be split into 2 chunks. | 2017-12-10 | 2017-12-10 | High | 5 | 28 | resolved | Bug solved during PP when discovered | ZhengRen,MingSheng | 1d00d66add7c3254450eb1ff2cd9f999b337277e
9 | 4 | header.jsp, bootstrapView.jsp and heatmapView.jsp | Home button path to the wrong location after a controller forwards to the page | relative paths changes after forward. | 10/13/2017 | 10/13/2017 | High | 5 | 33 | resolved | Bug solved during PP 4.17 when discovered | Brittany, Colin | 8b331a18addf63e63c27b2545e04ea509d92b452
10 | 4 | Bootstrap Update | Bootstrap Update not being able to insert Location.csv record into databse | Bootstrap update for additional Location file wrongly detects duplicate records | 2017-10-17 | 2017-10-17 | High | 5 | 38 | resolved | Bug solved during PP 4.23 when discovered | ZhengRen,MingSheng | 8b83b0c4755f1d5fe96de15d90387023903bdc93
11 | 4 | Bootstrap Update | Bootstrap Update view display wrong csv files under number of records added | Bootstrap upload view/display for additional files, shows number of records added for location as location lookup. | 2017-10-17 | 2017-10-17 | Low | 1 | 39 | resolved | Bug solved during PP 4.23 when discovered | ZhengRen,MingSheng | 8b83b0c4755f1d5fe96de15d90387023903bdc93
12 | 4 | Bootstrap | In BootstrapView.jsp additional spacing found between error messages for Demographic.csv, LocationLookup.csv and Location.csv | Additional <br> created in for loop | 10/19/2017 | 10/19/2017 | Low | 1 | 40 | resolved | Bug found in AWS debugging, resolved in PP 4.32 debugging session | ZhengRen,MingSheng | 895a5795c45de17aacbfff79fd623df53d9fbee3
13 | 4 | Top-K Next Place, Top-K Companion | LocationChunk class getOverlappingSeconds method does not work for chunks with exact same start time and end time. | lack of if statement to catch conditiion | 10/19/2017 | 10/19/2017 | High | 5 | 45 | resolved | Bug found in AWS debugging, resolved in PP 4.32 debugging session | ZhengRen,MingSheng | 895a5795c45de17aacbfff79fd623df53d9fbee3
14 | 4 | Breakdown by year and gender | JSON response for invalid token returns wrong error message | Wrong error message typed | 10/19/2017 | 10/19/2017 | Low | 1 | 46 | resolved | Bug found in AWS debugging, resolved in PP 4.32 debugging session | ZhengRen,MingSheng | 895a5795c45de17aacbfff79fd623df53d9fbee3
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
116

## Bug_Log_Iteration 5
Bug metric
No. | Iteration | Function | Description | Cause | Date Found | Date Solved | Severity | Points Allocation | Points Accumlated Per Iteration | Status | Action | Pair Programmers | Git Commit ID
1 | 5 | AGD | AGD failed to find groups where start or end times of the two users stays are exactly equal | LocationGroup/LocationChunk comparisons did not catch cases where start and end time for both objects are equal. | 10/24/2017 | 10/25/2017 | High | 5 | 5 | Resolved | Bug solved during pp session, task 5.1 | David, Brittany | 1cd3f56267cc45ffcf4aefcca18621a17000b950
2 | 5 | AGD | AGD failed to remove subset groups from final result | Problem with isSubset method in LocationGroup | 10/25/2017 | 10/27/2017 | High | 5 | 10 | Resolved | Solved during planned pp session, task 5.17 | David, Brittany | 49000bcabb053b85e005a0bf1502c26138c2a230
3 | 5 | Bootstrap | Missing token hidden field in bootstrapView.jsp | token hidden field commented out | 10/26/2017 | 10/27/2017 | High | 5 | 15 | Resolved | Solved during planned pp session, task 5.16 | David, Brittany | 838c5b2e84a3b97451b039bb3cef62b048b701fc
4 | 5 | TopK Next Places | Does not show % of people who went to a semantic place out of the total number of users | Did not have a column for the % of people | 10/26/2017 | 10/27/2017 | Low | 1 | 16 | Resolved | Solved during planned pp session, task 5.16 | David, Brittany | 838c5b2e84a3b97451b039bb3cef62b048b701fc
5 | 5 | AGD | AGD Processing takes too long | Inefficient process | 10/26/2018 | 10/27/2017 | High | 5 | 21 | Resolved | Solved during planned pp session, task 5.17 | David, Brittany | 49000bcabb053b85e005a0bf1502c26138c2a230
6 | 5 | TopK Companions | Type error for JSON service "macAddress" should be "mac-address" | Typo | 10/27/2017 | 10/28/2017 | low | 1 | 22 | Resolved | Bug found during AWS regression test, solved during planned debugging session task 5.22 | David, Brittany | 50102003ff8c5f7e3bb2146dd7cdcd9ed2c950d0
7 | 5 | Bootstrap | Did not handle duplicate entry records for both extisitng csv and additional csv | Overlook corner case | 10/29/2017 | 10/31/2017 | High | 5 | 27 | Resolved | To be solve during debugging session, task 5.26 | MingSheng,Brittany | 27352ef2469ea27798ed7d4f78d4837a678a833a
8 | 5 | TopKNextPlace | Could not display any result in NextPlace View, page is crashed. Showing nothing including page header | Results value will never be null because it has been initalized in the TopKNextPlaceController. Using results != null will always be true, therefore we have to check using .toString | 10/29/2017 | 10/31/2017 | Low | 1 | 28 | Resolved | To be solve during debugging session, task 5.26 | MingSheng,Brittany | 27352ef2469ea27798ed7d4f78d4837a678a833a
9 | 5 | Heatmap | Semantic Place not in alphabetical order | Did not sort according to alphabetical order | 2017-01-11 | 2017-02-11 | Low | 1 | 29 | Resolved | To be solved during debugging session | MingSheng,Brittany | 53fc4328e4ade5728c19d578944359e252c71d1a
10 | 5 | Bootstrap | Bootstrap testdata cannot be bootstrapped | Did not put continue; | 2017-01-11 | 2017-02-11 | High | 5 | 34 | Resolved | To be solved during debugging session | MingSheng,Brittany | 53fc4328e4ade5728c19d578944359e252c71d1a
11 | 5 | Bootstrap | AWS Bootstrap speed performance differ from local bootstrap performance | Change InnoDB to MyISAM (storage engine type) | 2017-02-11 | 2017-05-11 | Low | 1 | 35 | Resolved | To be solved during debugging session | Bihuang, MingSheng
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
116

## Iteration 6
Bug metric
No. | Iteration | Function | Description | Cause | Date Found | Date Solved | Severity | Points Allocation | Points Accumlated Per Iteration | Status | Action | Pair Programmers | Git Commit ID
1 | 6 | Login | Login usernamer should be username(acer.2016) instead of email address | Misunderstanding requirement | 2017-09-11 | 14/11/2017 | High | 5 | 5 | Resolved | Bug solved during pp session, task 6.03 | Bihuang & MingSheng | 4020e54b6b37eb005c76c1a0e12207a2fe952edf
2 | 6 | Breakdown by year and gender | Other years that does not have students must be shown and set to 0 | Wrong assumption required | 2017-09-11 | 14/11/2017 | High | 5 | 10 | Resolved | Bug solved during pp session, task 6.03 | Bihuang & MingSheng | 4020e54b6b37eb005c76c1a0e12207a2fe952edf
3 | 6 | PopularPlace | results instead of result , semantic-place instead of semantic_place | Wrong character formating | 2017-12-11 | 14/11/2017 | Low | 1 | 11 | Resolved | Bug solved during pp session, task 6.03 | Bihuang & MingSheng | 4020e54b6b37eb005c76c1a0e12207a2fe952edf
4 | 6 | JSON Authentication | Missed out to handle authentication in the POST method | Did not place the doPOST method | 2017-12-11 | 15/11/2017 | High | 5 | 16 | Resolved | Bug solved during pp session, task 6.04 | Bihuang & MingSheng | 29997c0dfe29cd3f1224d60d6019eea8fcfbc10c
5 | 6 | AGD | Failed to detect group with "ddddd..." and "eeee..." at 30-10-2017 12:14:59pm with uat-data2 data set | Problem with detecting subset when looking to see if a potential group has been attempted before | 2017-09-11 | 2017-11-16 | High | 5 | 21 | Resolved | Bug solved during pp session, task 6.05 | David & Zheng Ren | c82bdd5cbef922e37c93a7a42e4ab1780c2c989c
6 | 6 | Breakdown by year and gender | The value of year(2017) should be displayed as a Integer instead of String in JSON response | Value was added to JSONObject as String not Integer | 14/11/2017 | 2017-11-16 | Low | 1 | 22 | Resolved | Bug solved during pp session, task 6.06 | David & Zheng Ren | dac10c203ec739916e7c027f8165a3e56ffce090
7 | 6 | Breakdown by year and gender | JSON order of year should be in ascending order(2013 follow by 2014...etc) | Wrong method call of descendingKey | 14/11/2017 | 2017-11-16 | Low | 1 | 23 | Resolved | Bug solved during pp session, task 6.06 | David & Zheng Ren | dac10c203ec739916e7c027f8165a3e56ffce090
8 | 6 | Bootstrap | Spelling mistakes for blank fields for bootstrap function | Spelling | 17/11/2017 | 17/11/2017 | Low | 1 | 24 | Resolved | Bug solved during pp session, task 6.08 | David & Zheng Ren | f7ad98778ff310791a550d4b553f56717890d71d
9 | 6 | Breakdown by year and gender | advance view displays wrongly if only 1 option is selected | Table formatting error | 17/11/2017 | 17/11/2017 | Low | 1 | 25 | Resolved | Bug solved during pp session, task 6.09 | Zheng Ren & BiHuang | 5be46fb879dd4e3e74a8e9cf1d9c21caa4b4ff4f
10 | 6 | Topk Next place | No result showed for json request | The attribute of database name has been changed so that we can not get the value | 17/11/2017 | 18/11/2017 | High | 5 | 30 | Resolved | Bug solved during pp session, task 6.12 | Zheng Ren & BiHuang | 5398fec922d74375c409e18f21de1840cfcaae81
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
116

## Bug Metric
BUG METRIC
Formula: 1 x num (low) + 5 x num (high) + 10 x num (critical)
Iteration | Total Bugs | Total Low Impact | Total High Impact | Total Critical Impact | Unresolved Low Impact | Unresolved High Impact | Unresolved Critical Impact | Bug Metrics | Action Done | Severity | Description
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
2 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 23 | N/A | High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
3 | 12 | 3 | 7 | 2 | 0 | 0 | 0 | 58 | Further development stopped, bugs to be solved before proceeding. | Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
4 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 46 | Bugs resolved during planned debugging sessions
5 | 11 | 5 | 6 | 0 | 0 | 0 | 0 | 35 | Bugs resolved during planned debugging sessions | Points in Iteration | Action
6 | 10 | 5 | 5 | 0 | 3 | 0 | 0 | 30 |  | Points < 10 | Use the planned debugging time in the iteration.
7 | [7 empty] | 0 |  | Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
UAT | [7 empty] | 0
AUAT | [7 empty] | 0
Total | [7 empty] | 0