## Schedule Metric
Schedule Metric
Action Plan
| Iteration | Total Planned Tasks | Total Completed Tasks | Task Metric | Iteration 1 | Estimates are accurate, all tasks completed. No changes to Schedule
| 1 | 11 | 11 | 100%
| 2 | 21 | 23 | 109.5% | Iteration 2 | Estimates are faily accurate - Additional tasks for "pseudo codes" planned due to changes in standard iteration plan - Bootstrap Update function not completed, replanned for iteration 4, week 8
| 3 | 22 | 24 | 109.1%
| 4 | 31 | 31 | 100% | Iteration 3 | Estimates are fairly accurate. No tasks from future planned iterations were completed. Schedule will continue as planned. - Tasks for programming TopK Companions and Breakdown functions were not completed in planned sessions. Additional sessions were planned in the iteration - Task for pseudocoding AGD was not completed in planned session. Additional session planned in iteration - Additional tasks were added, involving updating diagrams, slides and AWS deployment (AWS learnt during class in this iteration). - Unresolved bugs outstanding in iteration 3, planned to be resolved at start of Iteration 4. Iteration 4 extended into buffer days to include tasks
| 5 | 26 | 36 | 138.5%
| 6 |  |  | #DIV/0!
| 7 |  |  | #DIV/0!
| 8 |  |  | #DIV/0!
| 9 |  |  | #DIV/0!
| 10 |  |  | #DIV/0! | Iteration 4 | Estimates are accurate, all tasks completed. No changes to Schedule - Additional debugging session 4.14 scheduled to fix bugs found during previous coding and debugging sessions. - Programming task for Bootstrap Update function found bugs, additional unplanned session to complete functionality scheduled
[5 empty] | Iteration 5 | Estimates are accurate, all tasks completed. No changes to Schedule - Able to resolve bugs during debugging session.
Iteration 6
Iteration 7
Documentation
Score(%) |  | Task Metric Action
TM < 50 |  | 1) Immediately, inform your supervisor about the slip within 24 hours. 2) Then use the same mitigation as the category 50 < TM < 90 and seriously consider dropping tasks. 2.Then use the same mitigation as the category 50 < SM < 90 and seriously consider dropping tasks.
50 < TM <= 90 |  | 1) Re-estimate the tasks for the future iterations. 2) Deduct the number of days behind schedule from buffer days. 3) If there is no more buffer day, decide the functionalities to drop.
90 < TM <= 110 |  | Our estimates are fairly accurate, and we are roughly on track. 1) Add/Deduct the number of days behind schedule from buffer days. 2) If there is no more buffer day, decide the functionalities to drop
110 < TM <= 150 |  | Gross over-estimated the effort required. 1) Re-estimate the tasks for the future iterations. 2) Add the number of days gained to buffer days.
150 < TM |  | 1) Immediately, inform your supervisor about the slip within 24 hours. 2 )Then use the same mitigation as the category 110 < TM < 150