## Slide 1: TEAM NULL G3-T2 Brittany Goh Chen Bihuang Tan Ming Sheng David Liu Chng Zheng Ren
App Demo & Progress Update
Notes: Introduce the group.

## Slide 2
1. Team Progress
2. Schedule
3. Critical Paths
4. Metrics
5. Role Rotation Plan
AGENDA

## Slide 3: 1. TEAM PROGRESS

## Slide 4: ITERATION 5 FUNCTIONALITIES PROGRESS
*Bootstrap
*Heatmap
Breakdown by year & gender
*Top-k popular places
Top-k companions
Top-k next places
Update Bootstrap
AGD
*Demo
Model-View-Controller (MVC) JSP Access Model 2
NOT plan to add / drop any functionality
Notes: The start date and end date of each iteration remains the same. The change in schedule is highlighted in red font. Delete Bid JSON is originally in iteration 5. However, due to timetable considerations, we decide to shift it from iteration 5 to iteration 4. We will touch on the reasons for the change later in our presentation.

## Slide 5: PM IMPROVEMENTS
Detailed Schedule Planning
Breaking tasks down further into sub tasks(e.g Code Bootstrap Update Functions in BootstrapServlet)
Notes: The start date and end date of each iteration remains the same. The change in schedule is highlighted in red font. Delete Bid JSON is originally in iteration 5. However, due to timetable considerations, we decide to shift it from iteration 5 to iteration 4. We will touch on the reasons for the change later in our presentation.

## Slide 6: PM IMPROVEMENTS
Detailed Schedule Planning
Planning future iterations in more detail(with specific week/date)
Notes: The start date and end date of each iteration remains the same. The change in schedule is highlighted in red font. Delete Bid JSON is originally in iteration 5. However, due to timetable considerations, we decide to shift it from iteration 5 to iteration 4. We will touch on the reasons for the change later in our presentation.

## Slide 7: PM IMPROVEMENTS
Detailed Schedule Planning
Better time estimation(balance between under/over plan)
Less unplanned/unfinished tasks
Notes: The start date and end date of each iteration remains the same. The change in schedule is highlighted in red font. Delete Bid JSON is originally in iteration 5. However, due to timetable considerations, we decide to shift it from iteration 5 to iteration 4. We will touch on the reasons for the change later in our presentation.

## Slide 8: PM IMPROVEMENTS
Debugging Process
Split functionalities testing and debugging session
Added in testing session after AWS deployment (Cloud Deployment Testing)
Notes: The start date and end date of each iteration remains the same. The change in schedule is highlighted in red font. Delete Bid JSON is originally in iteration 5. However, due to timetable considerations, we decide to shift it from iteration 5 to iteration 4. We will touch on the reasons for the change later in our presentation.

## Slide 9: 2. SCHEDULE

## Slide 10
Iteration 4
Start Date: 9/10/2017
End Date: 22/10/2017
PM: DAVID
Pair 1: Colin & Brit
Pair 2: MingSheng & Zhengren
TASK | MEMBER ALLOCATION
Design (Technical Documents) Update Class/Sequence Diagrams Update JavaDocs Standardize Test Cases | David
Programming Heatmap Bootstrap Update Location Chunk Utility AGD View Code JSON authentication | TMS & ZR TMS & ZR CBH & GMSB CBH & GMSB CBH & GMSB

## Slide 11
Iteration 4
Start Date: 9/10/2017
End Date: 22/10/2017
PM: DAVID
Pair 1: Colin & Brit
Pair 2: MingSheng & Zhengren
TASK | MEMBER ALLOCATION
Test Cases Heatmap Automatic Group Detection | TMS & ZR CBH & GMSB
Debugging Session Top-K Next Place Top-K Companion Heatmap Bootstrap Popular Place | CBH & GMSB TMS & ZR TMS & ZR TMS & ZR CBH & GMSB

## Slide 12
Iteration 5
Start Date: 23/10/2017
End Date: 5/11/2017
PM: MingSheng
Pair 1: David & Brit
Pair 2: Colin & Zhengren
TASK | MEMBER ALLOCATION
Design (Technical Documents) Update Diagrams App Demo Milestone Preparation Update JavaDocs | CBH TMS CBH & ZR
Programming AGD Beautify UI Application | DL & GMSB CBH & ZR
Test Cases Automatic Group Detection | CBH & GMSB
Debugging Session AGD | DL & GMSB

## Slide 13
Iteration 6
Start Date: 9/10/2017
End Date: 22/10/2017
PM: Colin
Pair 1: Colin & MingSheng
Pair 2: David & Zhengren
TASK | MEMBER ALLOCATION
Design (Technical Documents) Update Diagrams UAT Milestone Preparation | Colin
UAT Debugging Session Login Bootstrap Top-K Companions Top-K Popular Places Breakdown by year and gender Top-K Next Places Heatmap AGD | GBMS & TMS DL & ZR GBMS & TMS DL & ZR GBMS & TMS DL & ZR GBMS & TMS DL & ZR

## Slide 14
Iteration 6
Start Date: 6/11/2017
End Date: 19/11/2017
PM: Colin
Pair 1: Colin & MingSheng
Pair 2: David & Zhengren
TASK | MEMBER ALLOCATION
Testing Login Bootstrap Top-K Companions Top-K Popular Places Breakdown by year and gender Top-K Next Places Heatmap AGD | DL & ZR GBMS & TMS DL & ZR GBMS & TMS DL & ZR GBMS & TMS DL & ZR GBMS & TMS

## Slide 15
Iteration 7
Start Date: 20/11/2017
End Date: 26/11/2017
PM: DAVID
TASK | MEMBER ALLOCATION
Prepare for Final Presentation | CBH, GBMS, TMS, ZR, DL

## Slide 16: 3. CRITICAL PATHS

## Slide 17: ITERATION 3
Code Top-k Companion
(1 day)
Code
Breakdown (1 day)
Create PM Review Slides (1day)
Update Class Diagrams (1day)
Group Meeting (1 day)
Code UI (1day)
Code Top-k Place (1day)
(1 days)
Create Test case Breakdown & Top-k popular Place (1 day)
(1 days)

## Slide 18: ITERATION 3
Code Test case Top-k Companion Top-k Next Place
(1 day)
Pseudocode Next Place & Companion (1 day)
Update Heatmap & Sequence diagrams (1day)
Pseudocode Breakdown & Popular Place (1day)
Code Top-k Next Place (1day)
Code Top-k Companion (1day)
Pseudocode AGD (1day)
Pseudocode Heatmap & Code Breakdown (1 day)
Debug BLRS + Regression Test + Deploy to AWS (1day)
Pseudocode Breakdown & Popular Place (1day)

## Slide 19: ITERATION 4
Debug
Outstanding
bugs (1 day)
Code JSON authentication (1 day)
Heatmap
& AGD Test case (1day)
Group Meeting (1 day)
Integrate JSON authentication into app (1 day)
Code AGD View (1 day)
Code Location Chunk Utility (1 day)
Code Heatmap Function (1day)
Code Bootstrap Update (1day)
(3 days)
(4 days)

## Slide 20: ITERATION 4
Test/debug Heatmap
(1 day)
Update Sequence diagrams (1day)
Create Test case JSON Authentication Bootstrap Update (1day)
Test/debug JSON Authentication Bootstrap Update (1day)
Debug BLRS + Regression Test + Deploy to AWS (1day)
(1 days)
Update Javadocs (1day)

## Slide 21: ITERATION 5
Code AGD
(1 day)
Update diagrams (1day)
Beautify UI (2 days)
(1 day)
Test AGD (1 day)
Code Review (1 day)
Finalize demo
Slides
(1 day)
Debug AGD (1 day)
Regression test +
debug (1 day)
Deploy to AWS,
test + debug (1 day)
Update Javadocs
+ metrics
(1 day)
Group Meeting (1 day)
(5 days)
(5 days)
(5 days)

## Slide 22: ITERATION 6
UAT
Debugging
(3 days)
Update
Documentation (1day)
Debug BLRS + Regression Test + Deploy to AWS (1day)
Group Meeting (1 day)
Regression Testing (1 day)
(3 days)

## Slide 23: ITERATION 7
Prepare for Final Presentation
(1 days)
Final Presentation (1day)
Group Meeting (1 day)

## Slide 24: 4. METRICS

## Slide 25: TASK METRIC
ITERATION | TASKS PLANNED | TASKS COMPLETED | TM SCORE
1 | 11 | 11 | 100%
2 | 21 | 23 | 109.52%
3 | 22 | 24 | 109.09%
4 | 31 | 31 | 100%

## Slide 26: BUG METRIC
ITERATION | LOW IMPACT | HIGH IMPACT | CRITICAL IMPACT | Total Bugs | BUG METRIC
2 | 3 | 2 | 1 | 6 | 23
3 | 3 | 7 | 2 | 12 | 58
4 | 6 | 8 | 0 | 14 | 46
Formula: 1 x num (low) + 5 x num (high) + 10 x num (critical)

## Slide 27: 5. ROLES ROTATION PLAN

## Slide 28: ROLE ROTATION PLAN

## Slide 29: THANK YOU